## Cost_Benefit_Analysis
ROOFTOP SOLAR FEASIBILITY STUDY — UP MUNICIPAL UTILITIES
PM Surya Ghar Yojana Scheme ¦ Cost-Benefit Analysis ¦ 2025
Utility | Location | Capacity (kW) | Installation Cost (₹L) | Govt Subsidy (₹L) | Net Cost (₹L) | Annual Savings (₹L) | Payback Period (Yrs)
Agra Municipal Corporation | Agra, UP | 500 | 175 | 52.5 | 122.5 | 28.5 | 4.2982
Lucknow Nagar Nigam | Lucknow, UP | 750 | 262.5 | 78.75 | 183.75 | 42 | 4.375
Meerut Municipal Corp | Meerut, UP | 300 | 105 | 31.5 | 73.5 | 17.5 | 4.2

## NPV_IRR_Analysis
NPV & IRR ANALYSIS — 25 YEAR PROJECT LIFE
Utility | Net Investment (₹L) | Annual Cash Flow (₹L) | NPV @ 10% (₹L) | IRR (%) | Verdict
Agra Municipal Corporation | 122.5 | 28.5 | 142.3 | 18.2% | VIABLE ✓
Lucknow Nagar Nigam | 183.75 | 42 | 198.6 | 19.1% | VIABLE ✓
Meerut Municipal Corp | 73.5 | 17.5 | 89.4 | 17.8% | VIABLE ✓

## Subsidy_Mapping
PM SURYA GHAR YOJANA — SUBSIDY MAPPING
Scheme Component | Details | Subsidy Amount | Eligibility | Status
Central Subsidy | ₹30,000/kW up to 2kW; ₹18,000/kW for 2-3kW | Up to ₹78,000 | All households | Active ✓
State Top-up (UP) | Additional 30% on central subsidy | Up to ₹23,400 | UP residents | Active ✓
Net Metering | Sell excess power to grid at ₹3.5/unit | Variable income | Grid connected | Active ✓
Bank Loan (Collateral free) | Up to ₹2L at 7% interest rate | Loan facility | All applicants | Active ✓
Municipal Discount | Property tax rebate 10% for solar adopters | Tax benefit | UP municipalities | Proposed

## Implementation_Roadmap
PHASED IMPLEMENTATION ROADMAP
Phase | Timeline | Activity | Utility | Budget (₹L) | Status
Phase 1 — Planning | Jan–Mar 2025 | Site survey & feasibility assessment | All 3 utilities | 2.5 | Completed
Phase 1 — Planning | Jan–Mar 2025 | Subsidy application & documentation | All 3 utilities | 0.5 | Completed
Phase 2 — Procurement | Apr–Jun 2025 | Vendor selection & tender process | All 3 utilities | 1 | In Progress
Phase 2 — Procurement | Apr–Jun 2025 | Equipment ordering (panels, inverters) | All 3 utilities | 350 | In Progress
Phase 3 — Installation | Jul–Sep 2025 | Agra Municipal — 500kW installation | Agra | 175 | Planned
Phase 3 — Installation | Oct–Dec 2025 | Lucknow Nagar — 750kW installation | Lucknow | 262.5 | Planned
Phase 3 — Installation | Jan–Mar 2026 | Meerut Municipal — 300kW installation | Meerut | 105 | Planned
Phase 4 — Monitoring | Apr 2026 onwards | Performance monitoring & reporting | All 3 utilities | 1.5 | Planned